## Sheet1
Sr. No | Tasks List | Time | Remarks
1- | Create Blazor Projects like BlazorWeatherApp.Client, BlazorWeatherApp.Server, BlazorWeatherApp.Shared projects. | 30 Mins
2- | Define Shared Data Model (Defined weather conditions) | 20 Mins
2.1- | -Add Harsh/Dangerous Flags (Task 1- Set properties for giveen conditions) | 30 Mins
2.2- | -Add Acknowledgment Flag (Task 2-Set properties for giveen conditions) | 30 Mins
3- | Backend API Development (Data Provisioning) | 30 Mins
3.1- | -Hardcode Weather Summaries & Locations | 15 mins
3.2- | -Generate Test Data | 15 mins
4- | Blazor Client UI Development | 45 Mins
4.1- | -Create/Modify Weather Data Page (BlazorWeatherApp.Client) | 30 Mins
4.2- | -Implement Critical Data Highlighting Logic (Task 1) | 15 mins
4.3- | -Add Visual Legend (Task 1) | 15 mins
5- | Personalization and User Interaction (Task 2) | 30 Mins
5.1- | -Update Legend for Personalization | 30 Mins
6- | Styling, Responsiveness, | 30 Mins
7- | Code Review and Refactoring | 30 Mins | Use AI for cleaning & formatting codes.
8- | Testing & Troubleshooting | 1 hour | Ideal it should take 1 hour but due configuration issue at my end it took 4 to 5 hours.Used MS copilot for troubleshooting.